## Checklist
Checklist for disposable-free event
Task/Action | Details/Description | When | Responsibility | Status/Completion | Notes
Explore funding options | Research potential grants and sponsors for your disposable-free initiative | 3 months before event |  |  | Contact local environmental organizations, explore regional and public funding
Concept creation | Develop a simple and appealing concept for visitors and vendors, discuss scale, preferences and priorities | 3 months before event |  |  | Create visual materials to appeal to different groups
Identify partners | Identify and involve partners; suppliers, waste incinerator, city representatives etc | 3 months before event |  |  | Find checklist with potential partners on separate page
Source and negotiate with supplier/s | Source and negotiate with suppliers of e.g. reusable dishes, deposit system, dishwashing system, communications bureau etc. | 3 months before event |  |  | Strong leadership and clear onboarding is key to ensure commitment
Estimate needs for items | Calculate the number of reusable items needed (e.g., sales x 3 for glasses) | 3 months before event |  |  | Make sure to plan for potential increases in demand
Plan for dishwashing logistics | Plan for dishwashing logistics—rent a dish container or use local facilities. Have a backup plan. | 2 months before event |  |  | Have a backup plan in case of breakdowns
Clear communication | Provide clear, concise messaging for both participants and visitors. Repeat key info. | 2 months before event |  |  | Use concise, easy-to-understand language
Kick-off meeting on site | Arrange a kick-off and site visit on-site with all partners and stakeholders | 2 months before event |  |  | Check the site, test flows, provide information and identify challenges to handle
Ban single-use items | Avoid all single-use items, including flyers and giveaways | 2 months before event |  |  | Enforce this rule for all event areas
Introduce a fee for single-use items | Consider introducing a fee for single-use items to encourage reusable alternatives | 2 months before event |  |  | Consider a tiered system for single-use items
Consider external labor | Consider hiring external labor (e.g., volunteers via sports associations or similar) and prepare clear job descriptions | 2 months before event |  |  | Reach out to local volunteers or student organizations
Plan for waste sorting | Plan efficient waste sorting with clear signage and stations | 1 month before event |  |  | Ensure all waste stations are clearly marked
Evaluate the event beforehand | Set questions for post-event evaluation | 1 month before event |  |  | Write clear evaluation questions in advance
Promote the initiative | Use suitable communication channels to promote your disposable-free event initiative | 1-2 weeks before event |  |  | Send email to inform
On-site meeting | Review flows and address any last-minute changes | 1 day before event |  |  | On-site meeting to review flows, identify obstacles, and manage last-minute changes before the event
Monitor Logistics | Assign someone to oversee logistics and waste management | During event |  |  | A site manager, logistics manager, operational project manager or similar
Waste Station Supervision | Ensure waste bins and dishes collection are regularly attended to | During event |  |  | There need to be volonteers or similar attending the stations at all times
Dishwashing Supervision | Ensure enough staffing resources and smooth flows | During event |  |  | Assign a responsible person to supervise the dishwashing system
Monitor Flow | Observe flows and make adjustments as needed | During event |  |  | Observe flows of dishes, suppliers, vendors and visitors and quickly make changes if significant deviations occur
Ongoing Communication | Communicate the initiative in suitable channels and formats | During event |  |  | Organise a guided tour to stakeholders on-site. Communicate on SoMe platforms and invite media to report on-site
Behavioural Change | Recognize that behaviour change takes time | After event |  |  | Influence factors like information, exposure, and environment for short-term changes. Consistent initiatives over time are key to long-term shifts in norms and habits
Evaluate Financials | Assess the financial benefits of using reusable items vs. single-use | During/after event |  |  | Evaluate and summarize the financial benefits of using reusable items compared to single-use items
Document Learnings | Document the process and share insights to help others | During/after event |  |  | Consider writing a report or learning manual to disseminate results
Share Results | Communicate the event’s success and results to the public | During/after event |  |  | Communicate on SoMe platforms and do a pressrelease