## Checklist
Checklist for Green Music Network Meeting
Task/Action | Details/Description | When | Responsibility | Status/Completion | Notes
Programming | Decide purpose and expected outcomes. | Early planning phase |  | Not Started
Build the right partnerships | Identify partners with shared sustainability goals. | Early planning phase |  | Not Started
Build the right partnerships | Start early conversations on roles and contributions. | Early planning phase |  | Not Started | Clarify who does what and expectations.
Secure resources | Secure budget, venue, catering, speakers, tech, and staff. | 3 months before event |  | Not Started | Reserve venues, speakers and catering well in advance.
Choose relevant topic/s | Select relevant topic/s (e.g. food, energy, transport). | Planning phase |  | Not Started
Programming | Create a half-day format: case studies, discussions, networking. | Planning phase |  | Not Started | Define outcomes clearly before inviting participants.
Invite participants | Target a mix of decision makers, experts, businesses, support orgs. | 6-8 weeks before event |  | Not Started | Always include at least one real case study.
Invite participants | Create and send an engaging invitation by email, with a link to digital registration or via an invitation service such as Eventbrite. | 6-8 weeks before event |  | Not Started
Invite participants | Send email reminder. | 1 week before event |  | Not Started
Prepare a presentation | Prepare a presentation with agenda and key info. Use mixed formats (video, photos), polls and collect slides from speakers. | 1 week before event |  | Not Started
Facilitate a hybrid event | Test technical equipment and hybrid group discussion method in advance. | A few days before event |  | Not Started | Include backup solutions for hybrid setup.
Welcome participants | Send welcome email with practical instructions, send meeting link to digital participants | 1 day before event |  | Not Started
Run and Facilitate the hybrid event | Assign support staff for online groups and use interactive tools, via Mentimeter or similar service. | During event |  | Not Started | Polls and whiteboards help engagement.
Email follow-up to participants | Send a thank-you email with the presentation and clear information about next steps. | Immediately after event |  | Not Started
Evaluate and share results | Collect quick survey after the event, via Google Forms or similar service. | Immediately after event |  | Not Started | Keep survey short and easy.
Evaluate and share results | Organise team debrief and share lessons in short report, if applicable. | Within 1 week after event |  | Not Started | Share learnings openly with partners and public.