## Checklist
Checklist for Awareness Raising Conference
Task/Action | Details/Description | When | Responsibility | Status/Completion | Notes
Define theme & goals | Set overall theme, focus areas, and desired outcomes | 4–8 months before |  |  | Align with partners
Secure funding & budget | Identify sources, confirm budget, set cost frames | 4–7 months before |  |  | Include side events
Book venue/s & date/s | Confirm main venue and spaces for side activities | 4-6 months before |  |  | Hybrid option?
Technical equipment | Large screen, audio-visuals, livestream setup, translation if needed | 4–5 months before |  |  | Test 1 week before
Invite partners & speakers | Contact key stakeholders, experts, moderators | 4–5 months before |  |  | Aim for diversity
Develop programme | Main sessions, side events, breaks, networking slots | 3–4 months before |  |  | Share draft early
Communication plan | Save-the-date, invitations, website, social media | 3 months before |  |  | Use visuals & video
Registration system | Online form, participant categories, confirmation emails | 2–3 months before |  |  | Collect dietary needs
Catering | Sustainable, reusable tableware items, plant-rich options | 2 months before |  |  | Include side tastings
Side activities | Plan workshops, networking events, side sessions | 2 months before |  |  | Link to main theme
Pledge preparation | Draft text, prepare signing method, prepare visuals, website and registration form | 1 month before |  |  | Use as follow-up tool
Documentation | Photographer, video, note-taker, social media coverage | During event |  |  | Share quickly online
Evaluation & survey | Online feedback survey, partner debrief, lessons learned | 1–2 weeks after |  |  | Report back to partners
Follow-up & momentum | Share pledge results, updates, next steps | 2–4 weeks after |  |  | Keep network active